## FGP
K-500-178A-ON Project FGP Main Works Power Distribution
Contract Sign Date: 03.11.2017
Mobilization Completion Date: 28.02.2018
Construction Start Date: 07.03.2018
Planned Finish Date: October, 2020
Planned Manhours: 2 500 000 / as of 18 June 2019 Incident and Injury Free Spent 1 210 000 Manhours
Planned km : 7 500 000 / as of 18 June 2019 Incident and Injury Free Spent 3 050 000 km
OHPL № | Voltage Level | Excavation (m3) | Geotextile (m2) | Foundation (pcs) | Backfilling (m3) | Metal Tower (pcs) | RC Pole (pcs) | Gantry (pcs) | Disconnector switcher (pcs) | Conductor Strings (m) | OPGW (m)
L154 | 110kV | 13276.92 | 5760 | 68 | 13811.74 | 17 | 1 |  |  | 10200 | 3400
L155 | 110kV | 16581 | 5033.7 | 64 | 11655.4 | 16 | 2 |  |  | 9470 | 3160
L57C | 35kV | 119816.6 | 61298 | 346 | 118694.9 | 86 | 47 | 1 | 1 | 62800
L58C | 35kV | 124623.56 | 59676 | 338 | 123435.77 | 84 | 45 | 1 | 1 | 63070
L45C1 | 35kV | 1216 |  | 10 | 1265.9 | 2 |  | 1 | 1 | 2650
L45C2 | 35kV | 1216 |  | 10 | 1265.9 | 2 |  | 1 | 1 | 1210
L157 | 110kV | 110 | 784 |  | 142
L172T | 110kV | 2093.4 |  | 12 | 2073 | 3 |  |  |  | 1100 | 420
L173T | 110kV | 1983 |  | 16 | 1958.6 | 3 |  | 2 |  | 1330 | 440
L177 | 110kV | 39233.88 | 22424.4 | 148 | 38942.41 | 37 | 15 |  |  | 47410 | 7750
L178 | 110kV | 36963.92 | 20403.1 | 148 | 36611.04 | 37 | 15 |  |  | 47190 | 7750
DIVERSION OF L154 | 110kV | 566.2 |  | 4 | 582.4 | 1 |  |  |  | 651
DIVERSION OF L155 | 110kV | 566.2 |  | 4 | 582.4 | 1 |  |  |  | 636
L156 | 110kV | 1934.4 | 1449 | 8 | 1986.4 | 2 |  |  |  | 1554 | 890
L157 | 110kV | 1076.6 | 784 | 4 | 1102.6 | 1 |  |  |  | 1392 | 860
L171 | 110kV | 3336 | 1702 | 12 | 3394.3 | 3 |  |  |  | 12459.4 | 3410
L171T | 110kV | 864.4 | 692 | 4 | 890.4 | 1 |  |  |  | 1236 | 230
L176 | 110kV | 97 | 115 | [6 empty] | 4790.4 | 2100
L176T | 110kV | 864.4 | 692 | 4 | 890.4 | 1 |  |  |  | 1434 | 310
L182 | 110kV | 41587.67 | 27030.73 | 172 | 42158.93 | 43 | 31 |  |  | 54342 | 9000
L183 | 110kV | 48271.83 | 36115.48 | 204 | 49077.61 | 51 | 41 |  |  | 66258 | 11000
L184 | 110kV | 6519.57 | 4844.21 | 36 | 7319.73 | 9 | 11 |  |  | 12018 | 2000
L185 | 110kV | 5528.57 | 4232.5 | 24 | 5249.73 | 6 | 5 |  |  | 4806 | 1650
L186 | 110kV | 11427 | 7162 | 56 | 11658.1 | 14 | 9 |  |  | 10947 | 3750
L187 | 110kV | 14679 | 6848.81 | 84 | 14830.8 | 21 | 1 |  |  | 11253 | 3740
L188 | 110kV | 14235 | 8240.18 | 80 | 14558.7 | 20 | 1 |  |  | 11103 | 3690
TOTAL |  | 508668.12 | 275287.11 | 1856 | 504139.16 | 461 | 224 | 6 | 4 | 441309.8 | 65550
СW 1152806 (C1470407)_SR 1272805 FGP FGP Motor Road Crossing
Construction Start Date : 05.09.2017
Mechanical Completion Date: 30.12.2017
CROSSING No | Voltage Level | Excavation (m3) | Geotextile (m2) | Foundation (pcs) | Backfilling (m3) | Metal Tower (pcs) | RC Pole (pcs) | Surge arrester (pcs) | Conductor Strings (m) | Cable (m) | Armored FOC (m)
ELX-HHR-05 ELX-MR-A2-04 | 6kV | 20.2 | 72 |  | 21.85 |  | 5 | 6 | 560 | 105
ELX-HHR-09 ELX-MR-A2-06 | 6kV | 19.7 | 60 |  | 20.62 |  | 6 | 6 | 570 | 105
ELX-HHR-12 ELX-MR-A2-09 | 6kV | 21.2 | 63 |  | 22.05 |  | 6 | 6 | 630 | 100
ELX-HHR-14 ELX-MR-A2-12 | 35kV | 1097.04 | 616 | 16 | 1081.96 | 4 |  | 6 | 400 | 800
ELX-HHR-19 ELX-MR-A2-15 | 6kV | 35.65 | 131.7 |  | 37.3 |  | 5 | 6 | 380 | 105 | 185
ELX-HHR-32 ELX-MR-A2-08 | 6kV | 74.95 | 328.5 |  | 75.67 |  | 6 | 6 | 620 | 100 | 300
ELX-HHR-33 ELX-MR-A2-05 | 6kV | 18.7 | 60 |  | 19.18 |  | 5 | 6 | 520 | 100
ELX-HHR-39 | 6kV | 16.5 | 69 |  | 17.86 |  | 4 | 6 | 260 | 80
ELX-HHR-40 | 6kV | 30 | 117 |  | 29.17 |  | 7 | 6 | 790 | 100
ELX-MR-E2S-213 | 10kV | 4.4 |  |  | 4.86 |  | 4 |  | 447
TOTAL |  | 1338.34 | 1517.2 | 16 | 1330.52 | 4 | 48 | 54 | 5177 | 1595 | 485
CW1152806 FGP Motor Road Crossing
Start Date : 25.05.2017
Finish Date: 25.12.2017
CROSSING No | Voltage Level | Feeder No
ELX-MR-E2N-102 | 10kV | F-6
ELX-MR-E2N-107 | 10kV | F-17
ELX-MR-E2N-110 | 10kV
ELX-MR-E2N-112, ELX-MR-E2N-111 | 35kV | F-53ц / F-54ц
ELX-MR-E2N-113 | 10kV | F-17
ELX-MR-E2N-117, ELX-MR-E2N-06 | 10kV | F-23
ELX-MR-E2N-J2-04, ELX-MR-E2N-J2-105 | 10kV | F-26, F-21
ELX-MR-E2N-J2-103 | 35kV | F-53ц / F-54ц
ELX-MR-E2N-J3-001 | 10kV | F-1, F-16
ELX-MR-E2S-213 | 10kV | F-17
ELX-MR-SH-J1-01,ELX-MR-SH-J1-02, ELX-MR-SH-J1-03 | 6kV | F-2
ELX-MR-SH-J2-01,ELX-MR-SH-J2-02 | 6kV | F-7